## Sheet1
Steps Description	Dependencies	Components	Execution Method or Build	Notes	Build Time	Build Cost	T&C Amount
customer login	Woo	form	Add 1 field named Organization	use_profile too	1	75	75.00
identify customer role	Woo	registration form	use above field	maybe add to orders	2	75	150.00
customer service date	jQuery	Datepicker	on product single page	gist	1	75	75.00
order management customer	Woo	inherit of Woo	validate		1	75	75.00
Registered installer notes	custom	metabox on orders	new plugin	use vertycal plugin for base	5	80	400.00
Installer assignment	custom	use custom plugin	usermeta and meta query caps	link Woo roles to query caps	5	80	400.00
							0.00
							0.00
							0.00
							0.00
							0.00
							0.00
							0.00
							0.00
							0.00
							0.00
							0.00
							0.00
Estimated Cost							1,175.00